## Schedule1.0
PROJECT SCHEDULE & MILESTONE CHART
| Project Name : | I8243 MCS-48 Input Out Expander (UF+ Digital)
| Company : | Teradyne (Asia) Pte Ltd |  |  | Project In-charge :
| Customer Contact : | n/a |  |  | Project Description : | To verify I8243 is in good conditions as per SOW's key deliverables.
Start Date :
|  |  | WW38 | WW38 | WW38 | WW38 | WW38 | WW39 | WW39 | WW39 | WW39 | WW39 | WW40 | WW40 | WW40 | WW40 | WW40 | WW41 | WW41 | WW41 | WW41
S/N : | TASKS |  | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | NOTES
1 | Schedule (PMP) | [20 empty] | Planned
Actual
2 | Personal Skills Assessment ( Before start SEP )
3 | GIT setup
4 | Review schedule with Mentor
5 | Test lists
6 | Mid Term review meeting with Mentor
7 | Final review meeting with Mentor
8 | Test Program Coding (Offline) - Continuity Test
9 | Test Program Coding (Offline) - SPI Fixed Read
10 | Test Program Coding (Offline) - SPI DSSC Read
11 | Test Program Coding (Offline) - SPI nWire PA Read
12 | Test Program Coding (Offline) - SPI DSSC Write
13 | Test Program Coding (Offline) - SPI nWire PA Write
14 | Test Program Coding (Offline) - PLL Frequency Measurement - Frequency Counter
15 | Test Program Coding (Offline) - PLL Frequency Measurement - DSSC
16 | Test Program Coding (Offline) - PLL Frequency Trim
17 | Test Program Coding (Offline) - Sleep IDD
18 | Test Program Coding (Offline) - Static IDD
19 | Test Program Coding (Offline) - IDD Profile
20 | Test Program Coding (Offline) - Dynamic IDD
21 | Test Program Coding (Offline) - IDDQ
22 | Test Program Debug (Online) - Continuity Test
23 | Test Program Debug (Online) - SPI Fixed Read
24 | Test Program Debug (Online) - SPI DSSC Read
25 | Test Program Debug (Online) - SPI nWire PA Read
26 | Test Program Debug (Online) - SPI DSSC Write
27 | Test Program Debug (Online) - SPI nWire PA Write
28 | Test Program Debug (Online) - PLL Frequency Measurement - Frequency Counter
29 | Test Program Debug (Online) - PLL Frequency Measurement - DSSC
30 | Test Program Debug (Online) - PLL Frequency Trim
31 | Test Program Debug (Online) - Sleep IDD
32 | Test Program Debug (Online) - Static IDD
33 | Test Program Debug (Online) - IDD Profile
34 | Test Program Debug (Online) - Dynamic IDD
35 | Test Program Debug (Online) - IDDQ
36 | Correlation and Acceptance
37 | Wrap Up - SEP wrap up (ppt)
38 | Wrap Up - Personal Skills Assessment (After)
39 | Wrap Up - Upload final test program and correlation data to GIT ( check steps for best practise )
40 | Wrap Up Presentation- Schedule meeting with Mentor
41
42
43
44
45
46 | [21 empty] | Rev.
|  |  |  | Planned | [17 empty] | Dated
Actual
Holiday
Milestone 1: Midreview
Timeline :
Milestone 2: Bin 1 and correlated test program
Milestone 3: Project presentation
Milestones :
Formulas:
WW38 = [WW38]+1
WW38 = [Project In-charge :]+1
Project In-charge : = [WW38]+1
WW39 = [WW38]+3
WW40 = [WW39]+3
WW41 = [WW40]+3